## Slide 1: Overview of Construction Status
K. Akai (KEK)
Feb. 20, 2012
17th KEKB Accelerator Review Committee
Two topics are included in this talk:
  Recovery of KEKB rings from the earthquake
  Construction status

## Slide 2: Recovery of KEKB Rings from the Earthquake

## Slide 3: D5 power supply building
Wall panel fell down
Cables out of rack
Panels and floor in the control room

## Slide 4: LLRF in D5
20cm fell down
More than 10 LLRF control racks for 2 RF stations fell down with floor by 20cm. Cables under the floor also damaged.
Other 10 racks fell down by 1cm.
More than 30 racks have been removed. Most of the cables, some of which are directly connected to tunnel, were also removed.
Repair floors underway.
New LLRF system to be installed.

## Slide 5: Air-fin cooler on the roof for klystrons
AFC on D4 roof
Stands of air-fin coolers and base plates on the roof are damaged.
Damaged in D1, D2, D4 and D5.

## Slide 6: Klystrons
Stoppers deformed
Stoppers of klystron sockets are damaged (half of all 35 klystrons).
Klystron positions moved (almost all).
Pumping system successfully restarted, and vacuum in klystrons was healthy.
Stoppers are being reinforced.
High power test to be conducted.
Stoppers damaged
Position moved
Anchor bolts at cooling tower released
M. Yoshida

## Slide 7: Wiggler magnets in stock building
Magnets that were stocked in a building moved and collided each other.
Coils of some magnets seemed deformed.

## Slide 8: Wiggler magnets check after 3.11
Field measurement of all (~150) wiggler magnets was performed.
Fortunately, all magnets are found healthy.

## Slide 9: Beam pipe bellows
21 bellows in D1 were opened, and checked inside.
One of them had damage on three RF contact fingers.
It is suspected that it shrank due to the earthquake.
3 bellows in D11 were opened and checked inside.
One of them had damage on three RF contact fingers.
It is suspected that it shrank after expanded to almost its limit.

## Slide 10: X-ray check of all bellows planned
撮影条件
IPサイズ：3・1/3×12インチ
X線：110kV、5mA
距離：700㎜
露出：5sec
Damage inside bellows can be checked using X-ray without opening to the air.
All HER bellows will be checked this year.
Y. Suetsugu

## Slide 11: Bellows X-ray check

## Slide 12: Tunnel floor, wall, ceiling
↑ Water leak at D10 expansion joint ceiling
↓ Floor crack at the same expansion joint
Big gap (several mm) generated at expansion joints.
Alignment of magnets shifted accordingly.
↑ Floor crack at D11 expansion joint
↓ Floor crack at Fuji expansion joint

## Slide 13
Moved in the whole ring. In particular, as much as 4mm at the expansion joints between straight and arc sections. Re-alignment of whole ring is necessary.
Magnet group
Difference between before and after the earthquake

## Slide 14: Summary of the earthquake issues
Damages
  Serious damage on various components in power supply buildings, including klystron stands, air-fin cooling towers, LLRF, and monitor control system.
  Damages on components in the tunnel seemed lighter than those in the buildings.
  HER bellows had some troubles. Need investigation.
  The expansion joints in the tunnel moved, and magnets alignment changed.
  Other components such as radiation shields, cooling pipes, some magnets.
Recovery
  Urgent cures (vacuum leak check, field measurement, system check etc.) were done immediately.
  Fortunately, all wiggler magnets in stock buildings found healthy, according to field measurement.
  Large scale recovery work started after the supplementary budget for restoration and rehabilitation became available in January 2012.
  Investigation of damages still continues, including X-ray survey of bellows, high-power test of klystrons, etc.

## Slide 15: Construction Status

## Slide 16
FY2010
FY2011
FY2012
FY2013
FY2014
Beam pipes and vacuum components
Fabrication
Baking, TiN coating
Magnets and power supplies
Fabrication
Field measurement
Install, system check
Install, alignment, system check
Dismantle KEKB
Damping Ring
Components Fabrication
DR tunnel construction
DR buildings construction
MR buildings construction
RF system
Reinforce and rearrange
Cooling system reinforcement
Monitor & control,
Beam transport
Fabrication
MR infrastructure
SuperKEKB construction schedule
e+e- Injector
Injector low emittance
Upgrade and operation for PF/PF-AR
Revised on Feb. 10, 2012
R&D
QCS and IR hardware
Fabrication
Optics and hardware design, R&D
Install, system check
SuperKEKB
commissioning
T=0
in FY2014
(early 2015)
Install, system check
System check
Install, alignment, system check
KEKB stop,
Construction start
We are here

## Slide 17: Commissioning plan
Phase 1: commissioning with Beast II
  Start early 2015 in FY2014, and continues for about half an year.
  Hardware and optics tuning, vacuum scrubbing, BG study, and collision tuning will be performed.
  Target luminosity in this phase is 1x1034 cm-2s-1.
  Belle II solenoid is required to be implemented by then for the low beta beam tuning.
Phase 2: commissioning with Belle II
  Start at the end of 2015.
  Machine tuning continues to increase luminosity with Belle II data taking.
This plan is agreed between SuperKEKB accelerator and Belle II.

## Slide 18: Prioritizing for T=0
Emittance
  The design emittance is targeted from the beginning (T=0). Main Ring magnets, beam pipes, injection system, etc. should be completed by then. The Injector and DR should satisfy the low emittance at T=0.
by*
  Although we may start with detuned optics, by* should be squeezed in the commissioning phase in about half year. Necessary hardware to achieve design by* must be implemented by T=0.
Beam current
  Considering budget profile and schedule, about half the design beam current is targeted in the first commissioning phase.
  Some components as well as infrastructure needed for the design beam current may be postponed after T=0. However, works that are difficult to do after the commissioning, such as rearrangement of cavities, reinforce cooling pipes in tunnel, will be completed by T=0.
Bunch charge at Injector
  Charge requirement for Linac and DR is set to match the beam current increase (roughly, 1 nC at T=0, 2 nC at +1year, 4nC at +2 years). This is to make a clear target for the RF e- gun and e+ source R&D and the Linac and DR construction schedule.

## Slide 19: Beam Energy
Design
  Original design maximum energy is 11.05GeV at U(6S).
Recent request for higher energy
  Requirement to investigate feasibility and issues for higher energy more than 11.5 GeV to around 12GeV was given by Belle II last autumn. The high energy running, if any, will be after several years running at U(4S) ~ U(6S).
Investigation
  We investigated limitations from various components such as Linac, BT, QCS, Power supply for magnets, etc. Present attainable Ecm is 11.24GeV, limited by e- Linac and e+ BT magnets.
  In order to inject the electron beam to HER at the required energy for 12 GeV operation, there must be huge reinforcement of Linac (replacement of S-band with C-band, 7.571 -> 8.6 GeV; current estimation of cost is about 24 Oku-Yen).
  From the viewpoint of the cost and labor, energy ramp-up of HER is supposed to be more realistic, so we will study its possibility.
  Development of C-band units for Linac will also be promoted.

## Slide 20: Request from Belle II regarding high energy running of SuperKEKB
November 8, 2011
Dear Akai san, Enomoto san and Koiso san,
( cc to Oide san )
On behalf of the Belle II collaboration, we would like to ask you and the KEKB accelerator team to investigate the maximum possible obtainable center of mass energy of Super KEKB and the issues associated with achieving it.
A reason for this request is a recent discovery by Belle of the two charged bottomonium resonances in the Upsilon (5S) decays. This remarkable result likely means that we now enter a new era of heavy quarkonium physics for which Super KEKB can provide unique opportunities. In particular, based on Heavy Quark Effective Theory, we expect the existence of exotic bottomoinum states near and above the thresholds of B*B*bar, Upsilon (5S).
These states, however, cannot be produced in a single-pion transition from Upsilon (5S) due to G-parity conservation rule. The only possible way to produce them can be by the emission of a rho meson from highly excited Upsilon states, and therefore, the total CMS energy of about 12 GeV is necessary. We expect meaningful physics results with running at this high energy even in case of significant luminosity degradation.
Hence, we request Super KEKB group kindly provide us with the information regarding its feasibility and the issues associated with high energy running. It is our strong wish to understand the limiting factors of high energy running and to work with you to solve the potential problems if possible.
We thank you very much in advance and look forward to hearing from you.
Peter Krizan
Spokesperson, the Belle II collaboration
Hiroaki Aihara
Chair of the Executive Board, the Belle II collaboration

## Slide 21: Limitations for Higher Ecm
A
B
D
C
E
12 GeV
11.05 GeV; original Ecm, max
E={7.32,4.18}
4.364 GeV @ 860A
Power supply of LER main dipoles
11.8
11.6
QC1P(LER) 90%
QC1E(HER) 90% quench limit
11.24 GeV;
present attainable Ecm, max
e- Linac (present limit)
e+ BT magnets
(with replacing power supplies)
e- BT magnets

## Slide 22: Design Issues to be fixed
Optics and IR design
  Both sides of IR (300m Tsukuba) vacuum components and magnets production scheduled in FY2012.
  QCS fabrication should start in FY2012.
Sextupole scheme
  Rotation sextupole magnets are required in LER.
  In HER, normal sextupole and independent skew-sextupole may be OK at T=0.
BG, Collimation system, radiation shield
  BG estimation, movable masks R&D, investigating radiation going on.
Requirement for BPM detectors
  Specification and how many at T=0?
Injection scheme
  Synchrotron injection in HER?
Abort system
  Possible scheme to abort nano beam.

## Slide 23: Budget
FY2010 | FY2011 | FY2012 | FY2013 | FY2014 | Total
75.0 | 10.5 | 14.5 | 0 | 0 | 100.0
0 | 41.6 | 40.2 | 61.6 | 46.7 | 190.0
0 | 4.5 | 12.4 | 7.2 | 0 | 24.1
75.0 | 56.6 | 67.1 | 68.8 | 46.7 | 314.1
Supplied | Supplied | Submitted to the Diet | To be submitted to the Diet | To be submitted to the Diet | 
FY2010
FY2011
FY2012
FY2013
FY2014
FY2015
FY2016
Very Advanced Research SP (100 Oku-Yen)
Other budgets for construction (214 Oku-Yen)
Operation budget (continues - - - )
SuperKEKB commissioning
We are here
Budget
  Total construction budget is 314 Oku-Yen for Rings, Injector, and Belle-II.
  Most of the budget comes year-by-year based.
  Operation budget is expected in FY2014 and later.
VARSP
Others
Facility
Total
Status
Unit: Oku-Yen (~1.2M$)

## Slide 24: Human Resources
HR of KEK staff
  Change of permanent staff members from the last MAC
    Apr. 2011: One retired. Three newly hired. Two joined from other groups.
    July 2011: One joined from other group.
    Apr. 2012: Two will retire. Three expected to be newly hired. Some join?
  Senior staffs after retirement
  Young members at term positions
Other helps
  Collaborations going on
  KEKB operation crew (company persons) to help construction work
Situation of short HR seems getting better
Date | Status | Needed FTE | Available FTE of permanent staffs | Non-permanent staffs added
Dec. 2010 | under construction | 77 | 56 | 61
Apr. 2011 | under construction | 77 | 60 | 66
Apr. 2012 | under construction | 77 | 62 +some? | 67 + some?

## Slide 25: Vacuum system
Fabrication of vacuum components -> Talk by Y. Suetsugu
  Aluminum ante-chamber beam pipes for LER arc sections (700 pieces, 2km length) on going in FY2011.
  Bellows and gate-valves for arc and wiggler sections to be completed soon.
  Copper beam pipes for wiggler sections in LER and HER to be completed soon.
  Beam pipes, bellows and gate-valves in Tsukuba straight section for both rings to be ordered in FY2012 and 2013.
  Movable masks, SR and X-ray monitor chambers will be made in FY2013 and 2014. Currently, R&D is going on.
  Replacement of some HER components for higher beam current before or after T=0 depends on budget.
Baking and TiN coating system -> Talk by K. Shibata
  Deck for vacuum work in Oho has been rebuilt after old AMY detector of TRISTAN was removed.
  The first baking system and the first TiN coating station has been built in the vacuum deck.
  More sets of baking and coating stations will be built soon.

## Slide 26: LER beam pipe fabrication @BINP

## Slide 27: TiN coating machine
TiN coating machine (1st vertical type) in Oho experimental hall

## Slide 28: Magnet system
Fabrication of magnets
  Fabrication and field measurement of LER 4m dipole magnets is going on. They will be installed in tunnel in the first half of FY2012.
  Half-pole and single-pole wiggler magnets, LER V-steering magnets, some of Q magnets on going in FY2011.
Fabrication of power supplies for magnets
  Power supplies for main dipole magnets and wiggler magnets are going on in FY2011.
  Power supplies of medium and small power will be ordered in FY2012 or later.
  Power supplies for DR: some are ongoing, others will be in FY2012.
Alignment and tunnel measurement
  Measurement after the earthquake showed significant movement of tunnel.
  Introducing GPS system and investigating the ground (boring, etc.) going on.
-> Talk by H. Iinuma

## Slide 29: Dismantle Tsukuba straight section
Magnets and cables have been removed.
Old base plates were removed, and the floor has been cleared up.
Dismantle both sides of IR (D1 and D2) done.
Removed power cables

## Slide 30: LER new 4m dipole magnets
Field measurement set up
The first goods delivered to KEK.
Install test in the outer LER over existing magnets in the inner HER.

## Slide 31: Interaction Region
A lot of critical issues
  Optics design
  QCS design and fabrication
  IR hardware design and assembly
  Background
    Storage beam
    Injection transient, blow-up, mask, IR aperture
    Vacuum pressure at large beta (beam-gas)
  Error tolerance at local chromaticity correction and correction method
  Ripple of power supply
  Collision feedback
Will be presented in the following talks today:
  Dynamic aperture and IR modeling (A. Morita)
  Error Tolerance and Optics Correction (H. Sugimoto)
  IR Magnets (N. Ohuchi)
  Beam Background (H. Nakayama)
  IR Vacuum Chamber and Assembly (K. Kanazawa)
  Collision Feedback (Y. Funakoshi)

## Slide 32: RF system
Upgrade items
  Change to 1 klystron to 1 ARES cavity scheme to increase beam power
    Rearrange ARES cavities
    Change input coupler of the ARES to increase coupling b from 3 to 6
    Add klystrons, power supplies, HPRF and LLRF
  Cure for increasing HOM power -> Talk by Y. Morita
  Develop new LLRF -> Talk by T. Kobayashi
    Damaged LLRF in D5 by the earthquake will be replaced with new ones.
  Develop Damping Ring Cavity -> Talk by T. Abe
  Replace old components with new ones (klystrons, power supplies, etc.)

## Slide 33
B
E
C
A
A
B
C
A
B
C
D
E
E
D
C
B
A
D4
D5
D7
D8
D10
D11
LER
HER
ARES cavity
SC cavity
Klystron, HP&LLRF system
Crab cavity
2
2
2
1
2
2
2
2
2
2
2
2
1
1
2
1
Type “A” power supply (for two klystrons)
Type “B” power supply (for one klystron)
1
OHO
FUJI
NIKKO
F
E
A
B
C
D
C
B
A
D4
D5
D7
D8
D10
D11
2
2
2
2
2
2
2
2
2
2
2
OHO
FUJI
NIKKO
2
2
D
C
B
A
2
D
H
G
D
C
B
A
D
C
B
A
D
C
B
A
F
E
D
C
B
A
D
C
B
A
SuperKEKB (commissioning: T=0)
KEKB
Lower
power
E
1
E
1
Add 3 power supplies (done)
Relocate 6 cavities HER->LER (done)
Add 2 cavities (done)
4 cavities to be removed this year
5 spare klystrons to be installed this year
Replace 4 old VP-klystrons in D10 with new klystrons

## Slide 34: Relocate ARES cavities in D5
To convert 6 ARES cavities from LER to HER.
3 cavities in LER
3 cavities moved to HER
6 cavities
moved to HER (done)
(KEKB-D5): 6 cavities in LER
On the way
Done

## Slide 35
ARES cavity
SC cavity
Klystron, HP&LLRF system
Crab cavity
2
1
Type “A” power supply (for two klystrons)
Type “B” power supply (for one klystron)
F
E
A
B
C
D
C
B
A
D4
D5
D7
D8
D10
D11
2
2
2
2
2
2
2
2
2
2
2
2
2
2
D
C
B
A
2
E
F
D
2
2
F
E
2
F
E
D
C
B
A
H
G
F
E
D
C
B
A
D
C
B
A
More reinforcement of RF for design beam current (after T=0)
add 1 or 2 SCC
add 2 klystrons, HP&LL
add 2 more klystrons, HP&LL,
add 1 more power supply
add 2 more klystrons, HP&LL,
add 2 more power supply
OHO
FUJI
NIKKO
The reinforcement after T=0 depends on requirement, machine performance and budget.

## Slide 36: Monitors, Control, Beam Transport
Present status
  R&D on various monitor components including BPM detectors, bunch-by-bunch feedback system, X-ray monitors is going on.
  Fabrication of BPM electrodes, amplifiers for FB, etc. is going on.
  Design of beam abort system in progress.
Will be presented in the following talks:
  Beam diagnostics, Feedback systems (M. Tobiyama)
  Photon Monitors (J. Flanagan)
  Synchrotron Injection (T. Mori)
  Beam Abort System (T. Mimashi)
  Control and Timing System (K. Furukawa)

## Slide 37: Reinforce Cooling system
Need for increasing cooling power
  Three times for vacuum system (5MW→16MW).
  1.5 times for magnet system (10MW→16MW).
How to do this
  Four new buildings for cooling system will be built in FY2012〜2013.
  Cooling tower of existing system will be reinforced for higher current.
  Replace existing cooling pipes in tunnel with larger aperture ones to increase water flow.
Issue
  Replacing cooling pipes is necessary almost all around the ring. This may interfere various works in the tunnel such as installing magnets and beam pipes. Furthermore, some of the existing or newly installed magnets may need to be temporarily moved. This may cause schedule delay.
Measure
  Possible ways of doing this work with minimum interference are now being studied by various contractors. Design of cooling system and piping is also ongoing. They will give reports by the end of this March to help us decide the way and schedule of tunnel work.

## Slide 38
12M
9M
3M
6M
New buildings for cooling system
New buildings for power supply
To build 6M, an old building for PS main ring power supply will be dismantled.

## Slide 39: Damping Ring
Design
  Optics design is almost fixed.
  Remaining issue is to determine beam pipe cross section size from the view point of CSR and acceptance. -> Talk by H. Ikeda
Components
  Fabricating magnets and power supplies are ongoing as scheduled.
  Test beam pipes (aluminum, ante-chamber) is being made. Mass production will be planned in FY2012.
  R&D of DR cavity is going on. A prototype cavity will be completed in FY2011, and will be high-power tested soon.
Tunnel and buildings
  See, next slide.
Issue
  Since tunnel construction delayed for six months due to the earthquake, installation of components will start only one year before T=0. Schedule in FY2014 will be very tight with installation, cabling and piping, system check, etc.

## Slide 40: Damping Ring
DR tunnel construction delayed for six months due to the earthquake.
Installation can start after the inspection of buildings, only one year before T=0.
very tight schedule
in FY2014

## Slide 41: Summary
The earthquake caused some delay and additional works for SuperKEKB construction, but we manage to recover to be in time for T=0.
Design work and construction work are going on at the same time in consistent ways. But time limit for some critical designs will come soon.
So far, budget is supplied as planned, except for the delay due to the earthquake.
Shortage of human resources is getting better.
Construction is well ongoing, prioritizing for T=0.