## Slide 1: Main Ring Magnet System
Magnet design & measurements Installation, survey & alignment
M. Masuzawa
K. Egawa
Y. Ohsawa
H.Iinuma (new! Relatively young!!)
Power supply design, tuning
Installation & Cabling
N. Tokuda
T. Oki
T. Kawamoto
T. Sueno
Superconducting magnet
Design & measurements
N. Ohuchi
M. Iwasaki
H. Yamaoka
Z. Zong
Retired but still active,
no time to rest
R. Sugahara
K. Tsuchiya

## Slide 2: Contents
After the earth quake
  Tunnel Damage
    Visible mostly at the expansion joints
    Survey tunnel from inside and outside
  Damaged magnets in the storage area
Current status
  Magnet installation
  Field measurement
  R&Ds
    Rotation mechanism of the sextupole magnets
    Additional windings of the correction coils of the sextupole magnets
Activities for the fiscal year 2012

## Slide 3: I. After the earth quake
Data from Geospatial Information Authority of Japan (GSI)
Tsukuba 0.51m
Compared to Shimane (1000km away)
Tsukuba  -0.1m Compared to Shimane (1000km away)
Horizontal
Vertical
  Damages
    Tunnel: Visible mostly at the expansion joints
    Storage area: most magnets are supposed to be re-used
  Activities for recovery
    Survey tunnel from inside and outside

## Slide 4
Uneven floor
Few mm displacement
liquefaction phenomena
cracks
Just above outside
Magnet position shifts
in the horizontal direction
Comparison between
Nov. 2010 and May 2011.
8mm

## Slide 5
Magnet position shifts in the horizontal direction.
Comparison between Feb.2010 and June 2011.
Oho exp. hall
Fuji exp. hall
Y
X
Arrows not to scale
Max. deviation is about 3 mm in
both X & Y directions.
Direction changes
at the expansion joints indicated by red arrows.
[mm]
[mm]
The south arc
section
    Survey tunnel from inside and outside (1)
Another full-survey will start within few months.

## Slide 6
    Survey tunnel from inside and outside (2)
Monitor GAP distance at expansion joints
Measure Level by Hydrostatic water Level System (HLS)
Quick circumferential length measurement
Measure cracks depth on the wall.
Measure cracks on the floor at BELLE
Depth: 30cm~80cm, >1.2m
Not yet fixed!!

## Slide 7
    Survey tunnel from inside and outside (3)
work in progress
Feb. 13- Mar. 30
Soil surveying
Deformation meas. by
Global Positioning System
B1
S1
S11
S2
S3
S4
S5
B2
S6
S7
S8
S10
S9
boring
Method for Swedish weight sounding test
Now installing!
Five GPS antennas are mounted on the KEKB buildings, which can access to the tunnel
One GPS antenna is mounted on bldg.#3
GPS network is utilized for tunnel network!
Direct views
Trying

## Slide 8: Some magnets were damaged in the storage area
All of the KEKB Wigglers are needed at SuperKEKB
About 10 KEKB LER dipole magnets are needed at SuperKEKB
Before the earthquake
All needed
~10 needed

## Slide 9: Damaged in the storage area
After the earthquake
Wiggler Magnets:
  All of the wiggler magnets were checked by field measurements and confirmed to be OK. See next page
Dipole Magnets:
  Many of them are damaged and unusable.
  There are probably 10~15 healthy magnets, though they need to be checked by field measurements this year.

## Slide 10
KEKB wiggler : re-measurement
long coil
right coil
left coil
The KEKB wigglers were re-measured.
Two reasons are ;
The KEKB wigglers will be re-used in SuperKEKB. The maximum currents will be increased from 950 A ( Imax_KEKB ) to 1400 A.
The KEKB wigglers were taken out from the tunnel and were in storage. They collided with each other due to the big earthquake (Mar. 11-th 2011).
A rotating coil ( long, right and left coils ) was used for the measurement.
These 3 probes of the rotating coil had been well calibrated during the last measurement.
(A)
(B)
Measure absolute values of area (A) and (B)
Measure residual field : (A)+(B)

## Slide 11: Results: All KEKB-wigglers are OK.
(A)
(B)
Excitation check: (A), (B)
Residual field check: (A)+(B)
projection

## Slide 12: II. Current status(1)
2. KEKB wigglers & cables removed.
1. Magnets, cables and etc removed.
3. In all sections:
KEKB LER dipoles and dipole correctors removed from the tunnel.
SuperKEKB LER dipole positions surveyed and marked on the floor and base plates installed.
4. Installation of the 1st SuperKEKB magnet (LER dipole) in the tunnel.
Showing 4 completed items in the tunnel

## Slide 13
R-side
R-side
R-side
L-side
1. Tsukuba straight sections (L/R sides of the IP)

## Slide 14
3. A) Survey for the new (longer) LER dipole
magnets with laser tracker
3.B) Base plates (3/dople) installation
in progress.
LER inner ring
LER inner ring
LER outer ring
HER long dipole
in the way.
LER outer ring

## Slide 15
Over the HER dipole
Tight clearance (~6mm)
Go over the magnet!
Access road
4. Installation of the 1st SuperKEKB magnet (LER dipole) in the tunnel.
String, move and set !

## Slide 16
1st installation of the SuperKEKB magnet on Feb.7th 2012.
The main purpose of this installation was to debug the tools and methods for installing
the 4 m dipole over the 6 m dipole.
We installed 2 dipole magnets. The rest of the LER dipoles are scheduled to be
installed this year.
Done!
Feb.7th 2012

## Slide 17
skbLB_new
skbLB_new
SuperKEKB_LER_Barc : measurement status
111 / 142 dipoles have been delivered.
95 dipoles have been measured by a long flip coil system.
79 dipoles are in storage.
II. Current status (2)

## Slide 18
Excitation check
I [A] | Bcenter NMR [T] | Poisson | BNMR/Bμ=∞
730 | 0.1660075 |  | 0.9953
760 | 0.1728672 |  | 0.9955
800 | 0.1819504 |  | 0.9954
840 | 0.1910295 | 0.19035 | 0.9953
860 |  |  | 
assuming the energy ratio ELER/EHER = 4/7
cf. : Due to constraints of LINAC, the injection and QCS system,
ELER_max = 4.28571 GeV, EHER_max = 8.75875 GeV
k = 0.0561 & E = 4.28571 GeV
BL = 0.802 Tm

## Slide 19
bL[x] measured by long flip coil
average | 5024673.5
σ | 285.697
σ /average | 5.7e-05
measure 4 times at each point.
Their variation (example) is ;
Scan every 50mm step
Measure 0A, 500A, 700A, 800A as well.

## Slide 20
each measured / reference (#1) @ 860A
reference variation @ 860A :
st.[ t ] / st.[ t0 ]
No. of mag. | 95
average | 1.000114
standard deviation | 0.000132
No. of mag. | 95
average | 1.0002958
standard deviation | 0.000205

## Slide 21: R&Ds
Rotation mechanism of the sextupole magnets
Mechanical rotation :
-30<<30 degrees (over spec?)
24 sextupole magnets needed for LER (+ needed for HER?)
Additional windings of the correction coils of the ALL sextupole magnets (~100/ring)
Needs to establish faster way to wind coils
Dq = 0 degree
Dq = 15 degree
Work is needed to be done IN the tunnel!
(photo from KEKB. 20 turns/pole with a single wire )

## Slide 22
Worm gear
KEKB Sextupole (L=300 mm,~700kg) as a test load.
Rotation mechanism of the sextupole magnets
Gear teeth

## Slide 23
2.2 mm2
AWG 14
3 mm2
AWG 12
 We will try to wind an additional ~50 turns/pole efficiently on the poles of the magnets in the beam line.
Use of flat cables is being investigated.
Temperature rise for multi layer cases.
Additional windings of the correction coils

## Slide 24: Activities for the fiscal year 2012
Field measurement plan
LER new dipole : ongoing
new wigglers : from spring 2012
LER_Q ( Leff =0.5837 ) : from spring 2012
HER_Qx : from spring 2012
In the tunnel: many and many!
Field measurement
Preliminary, very
GPS network
etc…..

## Slide 25
✔36 KEKB wigglers scheduled to be installed in HER next month.
✔7 quadrupole magnets
replaced by shorter ones this year.
✔Two quads/tunnel
will be installed.
Totally new beam lines
Both ends of IR
✔Magnets, cables,,, scheduled to be removed.
In all sections:
✔LER dipoles (100),
LER vertical dipole correctors(~220),
LER wigglers (280)
scheduled to be installed this year.
In the tunnel
Two important keys :
Careful scheduling with a work of the vacuum/magnet cooling water system by the Plant and Facilities Department,
Control tunnel temperature at SuperKEKB operating value for precision survey and alignment!

## Slide 26
Thanks

## Slide 27
LER magnet | number | specification | status
Dipole B_arc, B_lc | 114 (+2) + 24 (+2) | fixed | being delivered
Wiggler : half / single pole | 112 (+2) / 56 (+2) | fixed | will be delivered in Mar. 2012
Short dipole | 2 | not yet | 2012
Q ( Leff =0.5837 ) | 20 | ≈ kb_Q.rf | will be delivered in Mar. 2012
QK ( skew Q ) | 10 | not yet | 2012
SL + skew Sx ( rotatable) | 8 + 24 | not yet | 2012
Vertical Corrector | ~ 220 | fixed | will be delivered
New magnets ( normal ) production status
2012.2.15

## Slide 28
HER magnet | number | specification | status
Dipole (4 m) ⊂ LER dipole | 13 | = LER B_lc | being delivered
BC* Leff = 0.3444 | 8 | not yet | 2012
additional kb wiggler | + 22 | fixed | ?
Q ( 0.56 m ) | 38 (+ 1) | ≈ kb_Q.arc | Contract process has started.
Q ( 1.12 m ) | 2 (+ 1) |  | Contract process has started.
Qx | 8 (+ 1) | ≈ KB_QX | delivered
QK ( Leff = 0.3444/0.3723 ) | 6 + 2 | not yet | 2012
SL + skew Sx (rotatable) | 8 + 24 | not yet | 2012
New magnets ( normal ) production status cont.
2012.2.15

## Slide 29
10 turns (x 10 A) = 100 AT are wound with the main coil.
These will be used to generate normal quadrupole field for beam-based alignment.
A request was made by the optics group to prepare additional windings to generate
skew quadrupole field.
Power supplies will be newly made for the additional coils.
Specifications have not been fixed yet. We will try to wind an additional ~50 turns/pole efficiently on the poles of the magnets in the beam line.
Use of flat cables is being investigated.

## Slide 30
Dq = 0 degree
Dq = 15 degree
Dq = -15 degree
Rotation by steeping motor
3 degrees/0.36 million pulses & 3 degree/gear tooth
Takes ~4 minutes to rotate 15 degree
Very smooth rotation up to ±10 degree
becomes heavier beyond ±10 degree
Rotation up to ±30 degree achieved
Reproducibility, coupling to the horizontal/vertical motion, stability etc, need to be checked (and probably need to be improved).
Handling of the power cables and cooling water pipes need to be examined.
Gear teeth
KEKB Sextupole (L=300 mm, ~700kg) as a test load.

## Slide 31
bL[x] measured by long flip coil
average | 5024673.5
σ | 285.697
σ /average | 5.7e-05
measure 4 times at each point.
Their variation (example) is ;

## Slide 33
Bldg.#3
6C
Look down view from the scope
Look up view from access road to the tunnel@6C
GPS Antenna
XY-stage
We made 8 pass-through holes on each top of building along KEKB ring

## Slide 34
✔36 KEKB wigglers scheduled
to be installed in HER
next month.
✔7 quadrupole magnets
replaced by shorter ones this year.
✔Two quads/tunnel
will be installed.
✔KEKB wigglers & cables removed.
Totally new beam lines
✔Magnets, cables and etc removed.
✔Magnets, cables,,,
scheduled to be
removed.
In all sections:
✔KEKB LER dipoles and dipole correctors
removed from the tunnel.
✔SuperKEKB LER dipole positions surveyed and marked on the floor and base plates installed.
✔LER dipoles (100),
LER vertical dipole correctors(~220),
LER wigglers (280)
scheduled to be installed this year.
✔ done
✔ to be done soon/this year