## Slide 1: Ring Commissioning
Y. Funakoshi
KEKB Review
2013. 03. 05

## Slide 2: Commissioning schedule
Start-up time of SuperKEKB
  SuperKEKB commissioning is expected to start in January 2015.
QCS schedule
  Due to the background issues, the fabrication schedule of QCS’s on the right side of IP will be delayed.
  SuperKEKB commissioning will start w/o QCS magnets.
Linac commissioning
  Linac beams are expected to be ready by the SuperKEKB ring commissioning.
Damping ring
  Commissioning of damping ring will start sometime after commissioning of SuperKEKB rings. (May or June 2015)
RF system reinforcement
  Works for reinforcements will continue in FY2015 and FY2016 due to budget constraint.

## Slide 3
Two possible scenarios
First target luminosity
1 x 1034 cm-2s-1
First target luminosity
1 x 1034 cm-2s-1
Scenario A
Scenario B

## Slide 4: Consensus between SuperKEKB accelerator group and Belle II group
To proceed with Scenario A (phase 2 commissioning with QCS and Belle II solenoid)
To keep Scenario B (phase 2 commissioning with QCS without Belle II solenoid) as a backup option for some unexpected situations.
This proposal by the accelerator group was accepted at the Belle II EB meeting on Sep. 27th.

## Slide 5: Procedures of machine commissioning
Commissioning I :Basic commissioning of machine (~ 1.5 month)
  Linac tuning
  Damping Ring tuning (new at SuperKEKB)
  BT tuning
  Injection tuning (including beam timing and simultaneous injection)
  COD correction, Optics correction (rough correction)
  Tuning on beam abort system
  Tuning on beam monitor system (including beam feedback)
  Tuning and measurement on radiation safety
  Tuning on other hardware systems
  Test and debugging various kinds of control softwares
Commissioning II : Vacuum scrubbing (>~3 months)
Commissioning III : More sophisticated tuning
  Optics measurements and corrections
    Squeezing IP beta function (more difficult than KEKB)
    Achieving a small x-y coupling (more difficult than KEKB)
  Beam collision tuning and luminosity tuning (more difficult than KEKB)
  Belle II beam background: study and tuning (more difficult than KEKB)
  Increasing beam currents (final target is higher than KEKB)
  Study on the other beam dynamics issues

## Slide 6: Vacuum scrubbing at KEKB （HER/LER）
HER
LER
HER
LER

## Slide 7
DR Commissioning
LTR commissioning 2 days
BPM commission
First turn 1 day
COD meas. and correction 2 day
BPM commission
Optics meas. 2 days
RTL commissioning 2 days
Injection to LER
25 Hz operation
SR commission
Vacuum scrubbing ~14 days
~ 3 weeks
by wishful thinking
SuperKEKB Commissioning Meeting 2011.11.08 Kikuchi, M.
~ 9 days
M. Kikuchi

## Slide 8: Commissioning phase 1 (2015 Jan. ~ May)
Machine condition
  No QCS, No solenoid (no Belle II)
Tuning items
  Special optics for phase 1
  Commissioning item I (basic commissioning)
  Commissioning item II (vacuum scrubbing)
    HER beam current ( ~< 1A)
    LER beam current (~ <0.5A with low emittance beam)
    Belle II people request enough vacuum scrubbing in this phase (before Belle II roll-in).
      At least one month with beam currents of 0.5 ~ 1 A.
  Damping ring commissioning (from May or June)
    If possible, we hope to check LER injection of the e+ beam from DR.
  Commissioning III
    Belle II Background study with Beast II Detector
    Achieving a small x-y coupling
      In phase 1, we can study without IR.
      Beam size monitor will have to work (with low beam current ~30mA?).

## Slide 9: Phase 1 - Linear Optics -
Optics W/O QCS and solenoid has been designed
QCS and solenoid is replaced by drift space.
Machine tuning except for IR is expected to be done in this phase.
LER
HER
Drift
Drift
H. Sugimoto

## Slide 10: Phase 1 - Dynamic Aperture -
DA example assuming, - Design bunch current. - 2% emittance ratio.
Beam loss estimation is ongoing from view point of radiation protection.
HER Touscheck Life ~6.3 hours
LER Touscheck Life ~1.4 hours
Funakoshi-san’s talk
Physical Aperture
RF Bucket
H. Sugimoto
Notes: Physical aperture LER 91*sigma
Physical aperture HER 48*sigma
rf bucket HER 36.07
rf bucket LER 33.89

## Slide 11: SuperKEKB beam-beam simulation
K. Ohmi
Smaller (single beam ) vertical emittance gives higher luminosity. Much lower vertical emittance than the design (about half) will be needed to achieve the design luminosity. A tentative target of x-y coupling w/o beam-beam is 0.15%.
Strong-strong method (PIC)
For the long-rage force, the gaussian distribution was assumed.
 | LER | HER
ex [nm] | 3.2 | 4.6
ey [pm] | 8.64 | 11.5
k [%] | 0.27 | 0.25
SuperKEKB design
SuperKEKB design luminosity
At SuperKEKB, low emittance tuning will be very important.
Lattice non-linearity and space charge effect is not considered.

## Slide 12: Comparison of emittances of colliders
Existing colliders
Future colliders
From Beam Dynamics Newsletter No. 31
Courtesy of F. Zimmermann, H. Burkhardt and Q. Qin
LEP3
TLEP-H

## Slide 13: Comparison of emittances of colliders [cont’d]
Existing colliders
Future colliders
LEP3
TLEP-H

## Slide 14: A Possible BEASTII Strategy
 | w/o QCS, w/o solenoid | w/ QCS, w/o soldenoid | w/QCS, w/ solenoid , No SVD, PXD
ECL shielding | N | N | N
Diodes & beam abort | Y | Y | Y
Micro-TPCs | Y | Y | Y, in dock
BGO | N | Y | ?
CDC prototype | N | Y | N
SVD, PXD ladders & monitors | N | Y | Y
Diamonds | Y | Y | Y
Modular design, where we can easily add/remove sub detectors as required
  Perhaps grouped into Inner BEAST, Outer BEAST
  Three configuration: T0, T1, T2
Inner Beast
Outer Beast
BEASTII-T0
BEASTII-T1
BEASTII-T2
All scenario
Scenario B
Scenario A
For BEASTII_T2, place some sub system in PXD DOCK space
Keep up development of all BEAST sub systems.
Y. Sakai
Phase 1
Phase 2
Phase 2

## Slide 15: Commissioning phase 2 (2016 Jan. ~ April)
Machine condition
  With QCS, with Belle II (no VXD)
  Full accelerator tuning, no physics run
  Target luminosity at the end of this phase: 1 x 1034 cm-2 s-1
Tuning items
  Injection tuning w/ Belle II detector starting from detuned optics
  Commissioning item II (vacuum scrubbing)
    Continue to increase beam currents
  Commissioning III
    Belle II Background study with Belle II (and with Beast II)
    Achieving a small x-y coupling with IR
    Squeezing IP beta functions
    Collision tuning with the nano-beam scheme
      Establishment of collision feedback
    Other beam dynamics issues
    Luminosity tuning

## Slide 16: Detuned Optics (4x8)
βx*: x4, βy*: x8, coupling =2 %, ξy ~ 0.025, ILER = 1 A.
The effect of intra-beam scattering is decreased in LER.
Example of Parameters for 1034 cm-2s-1

## Slide 17: Commissioning phase 3 (2016 Oct. ~ )
Machine condition
  With QCS, with Belle II including VXD
  Continue full accelerator tuning. Physics run will start after some detector tuning period.
Tuning items
  Commissioning item II (vacuum scrubbing)
    Continue to increase beam currents
  Commissioning III
    Achieving a small x-y coupling with IR?
    Squeezing IP beta functions
    Other beam dynamic issues
    Continue luminosity tuning

## Slide 18: Summary
The SuperKEKB accelerator ground and Belle II ground agreed that the ring commissioning will be done with 3 phases. There are two possible scenarios. Scenario A has the first priority. Scenario B is kept for the situation where Belle II schedule delays.
Phase 1 (scenario A) (2015 Jan. ~ May)
  No QCS, No Belle II
  Basic commissioning, vacuum scrubbing, low emittance tuning, detector background (Beast II), DR commissioning
Phase 2 (scenario A) (2016 Jan. ~ April)
  w/ QCS, w/ Belle II (no VXD)
  Full accelerator tuning, no physics run, detector background (Beast II)
  Target luminosity = 1 x 1034 cm-2 s-1
Phase 3 (scenario A) (2016 Oct. ~ )
  w/ Belle II (w/ VXD)
  Continue accelerator tuning, Belle II tuning, physics run will start.

## Slide 19: Future prospects
Tasks to be done (from summer 2013)
  More concrete and detailed scenarios for beam commissioning
  Development of operation software
Ask for your cooperation
  SuperKEKB is an extremely difficult machine
    Low-beta, Low-emittance, nano-beam scheme, high beam currents, high luminosity
  Pioneer for new accelerator physics
  Experiences in other laboratories are extremely helpful
    SLAC, BINP, DAFNE, , SuperB, Cornell….

## Slide 20: Spare slides

## Slide 21
Detailed Schedule 1
Scenario A
Scenario B

## Slide 22
Detailed Schedule 2
Scenario A
Scenario B

## Slide 23: Comparison of two scenarios during commissioning phase 2
 | Scenario A (w/ solenoid) | Scenario B (w/o solenoid)
Optics correction(1) Squeezing IP beta functions | We can do full tuning. | We can do something. But we will have to do tuning w/ Belle II solenoid almost from scratch.
Optics correction(2) Achieving a small x-y coupling | We can do full tuning. | We can do something. But we will have to do tuning w/ Belle II solenoid again anyway.
Collision tuning | We can do full tuning. | The beam collision may not be possible w/o Belle II solenoid.
Belle II background Study and tuning | The real beam background can be studied. Also some test detectors can be installed at the place of VXD. | Some studies can be possible.
Risk to Belle II | Maybe we can avoid the risks by adiabatic tuning (start from small beam currents, with detuned optics). | Less risk

## Slide 24: Comparison of two scenarios (cont’d) during commissioning phase 2
 | Scenario A (w/ solenoid) | Scenario B (w/o solenoid)
Works for accelerator setup | Less works. | One more QCS field measurement. (heavier load to QCS group)
Cosmic-ray run w/ VXD | Less time before phase 3. Can also be done in the beginning of phase 3. | More time before phase 3.
Expected time for the first target luminosity (1 x 1034 cm-2s-1) | Earlier (maybe during phase 2). | Later (3〜5 months after phase 3 start).

## Slide 25: Commissioning III : More sophisticated tuning
Optics measurements and corrections (1) : squeezing IP beta functions at IP
  We will squeeze the IP beta functions with observing the beam lifetime, the injection rate and the Belle II background. This study can be done with small beam currents (~30mA).
  QCS’s are vital for this study. We can do something without solenoid (Belle II). However, we need to start tuning with solenoid (Belle II) almost from scratch.
  This tuning is most important for the luminosity at SuperKEKB. A factor 20 of the luminosity gain is expected by squeezing beta functions.
    The first target of vertical beta function at IP (by*) is 10 times larger values of the design values.
Optics measurements and corrections (2) : achieving a small value of x-y coupling
  We need to measure the beam size with x-ray monitor.
    The beam size measurements will be possible with small beam currents with relatively high bunch currents.
    We do not need the solenoid winding for clearing the electron clouds.
  Although it is worthwhile to do this study w/o Belle II solenoid, we also need to do the study also with Belle II solenoid.
Collision tuning
  We have no experience on the beam collision with Nano-beam scheme.
    Finding beam collision, establishing orbit feedback system（including dithering system）
    Luminosity tuning like at KEKB (this kind of tuning will continue many years.)
  It is worthwhile to do this tuning w/o solenoid. However, there is a possibility that the beam collision will not be possible w/o Belle II solenoid.
Belle II (Beast II) background study, tuning

## Slide 26
Revised on April 1st 2012

## Slide 27: Facilities
Storage and staging areas needed for magnet and vacuum components.
Need increased cooling water for klystrons and magnets:
  24 klystrons for ARES cavities, 8 klystrons for SCC
  Magnet cooling water needs double (4 plants -> 8)
Electricity:
27
KEKB/KEK total
Electricity Consumption: June-09
(Design option) | KEKB:MW | ΔMW | KEK:MW | ΔMW
Present(Average) | 45 |  | 64 | 
Nano Beam: June-09 | 70.7 | 24.3 | 96 | 32
Upgrade: Feb.-09 | 94.8 | 49.8 | 120 | 56
Super: ‘07-July | 102.6 | 57.6 | 128 | 64
Recent Design(Feb.-10): Add 2 ARES units--> +(3~4)MW
M. Ono