## Slide 1: Construction of the Interaction Region
The 18th KEKB Accelerator Review Committee
KEK, 4-6 March 2013
K. Kanazawa
for
KEKB Vacuum Group
IR Technical Meeting Member
IR Installation Meeting Member
SVD/IR Mechanics Meeting Member
QCSR
VXD unit
Support extension
IP Chamber
CDC
Inner
tube

## Slide 2: Contents
Sketch of the interaction region
Mile-stones and task schedule
Bridge reinforcement
Installation scenario
Vacuum around IR
IP chamber
Radiation shield
Summary

## Slide 3: Sketch of the Interaction Region Phase 2
Belle 2
IP
QCSL
QCSR
Moving stage
Slide gate shield
Positron
Electron

## Slide 4: Sketch of the Interaction Region Phase 1
Temporal shield
(on the temporal stage)
Al IP chamber
(ID 4 cm, ~2 m long)
Copper ducts with BPM
Moving stage without QCSL support
Fixed temporal stage

## Slide 5: Mile-stone and Task Schedule
 | date | Belle rotation | QCS | Special magnets | Bridge reinforcement | QCS support and Moving stage | IP chamber | Ta beam pipe for QCS | Vacuum system | Installation scenario | Back ground estimation and Radiation shield | LABM | Luminosity monitor
 |  | Belle | MG(Cryo) | MG | MG | MG | Belle/VAC | VAC/MG(Cryo) | VAC | Belle/VAC | Belle/RSC/Acc | BM | Belle/Acc
Now | - Mar 2013 | Complete first stage | QCSL under fabrication |  | Decision |  |  |  |  |  |  | Fix position | 
 | Apr 2013 - Feb 2014 |  | QCSR fabrication start QCSL complete |  | (Must end before Oct 2013) | Bridge work L side complete | Ver. 1 final fabrication |  |  | Select scenario |  |  | 
QCSL test at IR | Mar 2014 - Aug 2014 |  | In situ test of QCSL |  |  | Mechanical test (L side) |  |  |  |  |  |  | 
 | Sep 2014 - Dec 2014 |  |  | Installation |  |  |  |  | complete |  | Phase 1 shield complete | Set up complete | 
Phase 1 | Jan 2015 - May 2015 |  | QCSR complete? |  |  |  |  | complete |  | Preparation complete |  | System test | 
 | Jun 2015 - Dec 2015 | Final adjust | QCS installation |  |  |  |  |  |  | 1 st test | Phase 2 shield complete |  | 
Phase 2 | Jan 2016 - Apr 2016 |  |  |  |  |  | Beast Feedback to var. 2 ? |  |  | Improvement |  |  | 
 | May 2016 - Sep 2016 |  |  |  |  |  |  |  |  |  | additional |  | 
Phase 3 | Oct 2016 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: Bridge Reinforcement
65 Hz
H. Yamaoka
The end of the bridge where QCS lies on is mechanically weak. For example the vertical oscillation of the place with 65 Hz is one of the lowest modes of the bridge oscillation.
The measured amplitudes during KEKB are tolerable if QC1E and QC1P oscillate with the same phase (this is the most probable case).
However. if a simple and effective way of reinforcement of this part is available, it should be done.
The chance of the work is quite limited. The decision should be done as soon as possible.

## Slide 7: Installation Scenario Basic conditions
IP chamber is supported by VXD frame.
  Both sides of IP chamber are fixed to the VXD frame transversally and are free longitudinally.
VXD is supported by CDC.
  The R-side of VXD is aligned transversally and is free longitudinally.
  The L-side of VXD is fixed to CDC.
QCS cryostats can move out.
Connection flanges for vacuum chambers.
Little work space to access flanges.
It is impossible to connect flanges by hands in this configuration.
Some work spaces to access flanges.
It will be possible to make use of these spaces.
Top view
CDC

## Slide 8: Installation Scenario - Baseline
T. Kohriki

## Slide 9: Installation Scenario Alternative Scenario with Remote vacuum seal mechanism.
Some people feel uneasy on the situation that VXD unit is pushed by QCS in the baseline scenario.
They proposed an alternative scenario to slide VXD with manual force and a remote vacuum seal mechanism.
The mechanism is not yet valid with a mock-up test.
However the choice of the installation scenario has various impacts on detailed designs of VXD and surrounding components.
The decision on the choice cannot be delayed so long.
DESY

## Slide 10: Vacuum around IR Layout of vacuum components near QCS in the R side
The beam pipe in the cryostat is made of Ta (red part in the figure). The maximum thickness of this pipe is 4 mm.
Pumps are located outside the cryostat.
The major gas load for the incoming positron line is photon-desorbed gas. That for the outgoing electron line is thermal outgassing.
electron
positron
Ta beam pipes will be coated with Au or Cu to reduce ohmic power loss.
Electron cloud in the cryostat beam pipe is expected to be suppressed by solenoid fields (~50 G is necessary).
SR power ~ 1.4 kW

## Slide 11: Vacuum around IR Typical cross section of Ta beam pipe
Vertically elongated aperture in QC1P
(Larger aperture is preferable but it is not available in the present design.)
BPM

## Slide 12: Vacuum around IR Layout of vacuum components near QCS in the L side
The layout is similar to the R side.
electron
positron

## Slide 13: Vacuum around IR Rough estimation of pressure near IP
The difference between P0 and PIP is determined by the local outgassing and the conductance of the beam pipe. It doesn’t depend on the pumping speed outside the cryostat.
Example: Incoming positron line
Assumptions:
  The equation for a long tube gives good estimation for a short tube
  At IP pressure is maximum
  P0 is determined by the total outgassing of the cryostat beam pipe and the pumping speed there (50 l/s).
  The thermal outgassing rate is 1×10-11 Torrl/s/cm2 (1.33×10-8 Pa m3/s/m2).
PIP
P0
positron

## Slide 14: Vacuum around IR Test Ta beam pipe
Ta pipe model for QCS with cooling path in the wall. This pipe has a weld seam between water and vacuum. The test with tap water caused no leakage at least for months.
Thermal outgassing of the Ta pipe. ‘Very low’
(H. Hisamatsu)
A test Ta beam pipe with cooling channels, a taper, and conflat flanges was fabricated.

## Slide 15: Vacuum around IR Photon-induced desorption of Ta, Au, and Cu (2nd)
Photo-desorption coefficients of Cu, Ta, and Au-coated Ta. Ta and Au-coating have a sufficiently low photo-desorption coefficient.
(At PF BL21, ecr = 4 keV, by Y. Tanimoto)

## Slide 16: Vacuum around IR Consideration on IR pressure
At least, the pressure around the IP (5m) must not affect the overall average design pressure of the ring (110-7 Pa). Therefore the target pressure in this region must be less than 1  10-7  3000/10 =3  10-5 Pa. A consideration on the beam-gas Rutherford scattering requires much lower pressure in the QC magnets where b is large.
The main gas source in this region is photon-desorbed gas due to the direct SR from the last bend. If a photo-desorption coefficient h is assumed to be 1  10-6 molecules/photon, The average pressure of this region will be a few  10-6 Pa.
It was shown that Ta and Au-coating have a sufficiently low photo-desorption coefficient. It was also shown Ta has a very low thermal outgassing rate.
Still we are looking for an idea to improve IP pressure.

## Slide 17: IP Chamber Cut View
Electron
Positron
S. Koike

## Slide 18: IP Chamber Design feature
HIP = Hot Isostatic Pressing
10~20 mm
The central straight part consists of double tube. Paraffin runs between them.
The connection between double tubes is done by Ti-Ti EBW.
1~2 mm
1~2 mm

## Slide 19: IP Chamber R&D
Done
  Stress analysis
    For the temperature difference between the two tubes at the center.
    Changing support position of beam pipe
  Fabrication test
    Precise machining of Be pipes
    NC machining of ridges
    Be-Ti brazing
    Ti-Ta HIP
    EBW near by HIP
    Pulsed sputter coating of Cu inside 2 cm Al pipe and its uniformity check
To be done (in preparation)
  Stress analysis
    Check the strength under dynamic force
  Fabrication test
    Au coating on Ti pipe
    Effect of EBW on the coating
    Simulation welding between inner and outer Ti pipes
Ta part will be fabricated in FY 2013 and the first version of IP chamber will appear within FY 2013

## Slide 20: IP Chamber Cooling
WL: 210W (Ta)
WL: 190 W (Ta)
SRQ: ~ 50 W
SRB: 100 W
WL: 70 W (bulk Au)
SRQ: few W
WL: 140 W (Ta)
WL: 270 W (Ta)
SRQ: ? W
SRB: 130 W
The coolant is paraffin. The flow of paraffin can absorb a heat of ~270W for a temperature rise of 10℃.
e
e+
Heat: 400 W.
Water cooling, ID 4 mm, L = 600 cm, v = 2 m/s
DT of water ~ 4C
Heat transfer coefficient to water: 1.1104 W/m2/ C
DT ~ 5 C (between water and pipe)
T. Kohriki
Ta will be coated with Au or Cu to reduce the wall loss.

## Slide 21: IP Chamber Are steep ridges permissible?
Gentle ridge
Steep ridge
Since the height of the ridge is only 0.5 mm, structures of impedance due to the sharpness of ridges appears in higher frequencies than a 6mm bunch spectrum.
Steep ridges are OK.
(K. Shibata, Y.H. Chin)
New ridge

## Slide 22: IP Chamber Tip scattering on a ridge
CHESS (Cornell Univ.) G2 beam line
Photon energy : 9 keV
Slit : 2 mm (H) by 0.05 mm (V)
Detector angular resolution : 0.2 degree (FWHM)
Ratio of the scattered photon. The slope of the taper inside the pipe is 1.23 degree.
T. Ishibashi, et al
Ta sample
Set up

## Slide 23: Radiation shield Phase 2
The present design seems insufficient to keep the experimental hall free from radiation.
(H. Nakayama and T. Sanami).
Further investigation is necessary.
There are two major radiation sources in the interaction region. One is the LER horizontal collimator (upstream) to cut the halo created by Touschek effect. The other is the downstream LER beam pipes hit by off-momentum positrons and gamma rays due to the radiative Bhabha process.
(Y. Funakoshi, Y. Ohnishi)

## Slide 24: Radiation shield Phase 1
Now on-going estimation of the beam loss at phase 1 suggests this structure is sufficient for Phase 1.
(Y. Ohnishi, T. Sanami)

## Slide 25: Summary
With the progress of the construction of SuperKEKB, the number of tasks to be solved for the interaction region is increasing.
Among them,
  We must make decision on the bridge reinforcement as soon as possible.
  The choice of the installation scenario has verious side effects. It cannot be delayed so long.
And,
  We are still looking for an idea to improve IP pressure.