## Slide 1: TiN Coating and Baking of Beam Pipes
The 18th KEKB Accelerator Review Committee
March 4, 2013
Kyo Shibata (on behalf of KEKB Vacuum Group)
KEKB Oho Lab. (2013.2.27)

## Slide 2: Introduction 1
What should we do before the installation of new beam pipes?
  For HER (e-) : Baking at the laboratory(not in-situ)
  For LER (e+) and Damping Ring : Baking & TiN coating at the laboratory
How many beam pipes should be processed?
  For HER (e-) : 180
  For LER (e+) : 1000 (of which  25 have electron clearing electrodes and TiN coating is unnecessary. )
  For Damping Ring : 100
Pre-installation works (coating and baking) started on last April.
  Pre-installation work means:
    Bringing beam pipes to KEKB Oho Lab. from storage area -> Coating (only for LER, 3days) -> Baking (3days) -> returning the beam pipes to storage area
  Large-scale works by 10 workers with 4 coating equipments and 4 baking equipments started on last September.
2013/3/4 the 18th KEKB Accelerator Review Committee 2

## Slide 3
2013/3/4 the 18th KEKB Accelerator Review Committee 3
3-go-kan Bldg.
(You are here.)
Storage area
KEKB Oho Lab.
Returning the beam pipes to storage area
Bringing beam pipes to KEKB Oho Lab. from storage area
TiN Coating
Baking
LER beam pipe without electrode
Visual check on the beam pipe
HER beam pipe
LER beam pipe with electrode
Assembling
(NEG pump & BPM electrode)
Flow chart of
pre-installation work
KEKB Oho Lab.

## Slide 4: Introduction 2
What we did after last KEKB Review are
  Setting up 2 more baking equipments and 4 coating equipments (vertical).
  Large-scale work in this facility. (This will continue this year. )
  Setting up 3 horizontal coating equipments for bent beam pipes. (in progress now)
Topics discussed in this talk are
  Baking & TiN coating facility, Evaluation of TiN coating, Status report on baking and coating works and Future plan.
  Working Schedule
2013/3/4 the 18th KEKB Accelerator Review Committee 4
Last year
Now

## Slide 5: Layout of Oho laboratory 1
4 baking equipments : 2 long type (5 m) and 2 short type (3 m)
5 vertical TiN coating equipments (for straight beam pipes. one of them is back up.)
3 horizontal TiN coating equipments (for bent pipes. In preparation now. )
2013/3/4 the 18th KEKB Accelerator Review Committee 5
16m
16m
Oho experimental deck (top view)
6.5 m
4.5mm
Baking equipment (long type)
Baking equipment (long type)
Baking equipment (short type)
Baking equipment (short type)
Coating equipments (vertical type)
Coating equipment (horizontal type)
Coating equipment (horizontal type)
Coating equipment (horizontal type)
stairway
stairway
Clean room

## Slide 6: Layout of Oho laboratory 2
View from different place.
2013/3/4 the 18th KEKB Accelerator Review Committee 6
16m
16m
6.5 m
4.5mm
Baking equipment (long type)
Baking equipment (long type)
Baking equipment (short type)
Baking equipment (short type)
Coating equipments (vertical type)
Coating equipment (horizontal type)
stairway
stairway
Clean room
Coating equipment (horizontal type)
Coating equipment (horizontal type)

## Slide 7: Baking 1 : Equipment
Hot-air heating method was adopted.
  Two beam pipes are mounted up and down in one hot-air oven.
  Hot-air oven consists of movable insulated walls and insulated frame.
  Hot air is circulated in the hot-air oven.
  Each pipe is evacuated by a turbo-molecular pump (0.3 m3/sec) during the baking.
2013/3/4 the 18th KEKB Accelerator Review Committee 7
Movable walls
Beam pipe
(double decker)
Pumping unit
Hot-air circulator (7.5 kW)
Now baking
Short type
Long type

## Slide 8: Baking 2 : Baking conditions
Baking conditions
  Temperature : 150 C (120 C for beam pipes with electrodes)
  Baking period : 26 hours
    It was confirmed that the temperature of the beam pipes in the oven became 150 C within a several hours if the temperature setting of the hot-air circulator was 175 C.
  Targeted pressure after baking : < 10-7 Pa
  NEG pump is activated at the same time.
Before baking
  TiN coating (if necessary)
  Installation of NEG pumps and BPM electrodes at Oho clean room.
After baking
  Filling with dry nitrogen up to atmospheric pressure.
  Isolating the beam pipe and putting a blank flange on the beam pipe.
  Keeping the beam pipe in the storage area until the installation.
2013/3/4 the 18th KEKB Accelerator Review Committee 8
Storage area (Oho lab.)
Clean room

## Slide 9: Baking 3 : Rate of baking output
Baking work started on last April.
  Baking work started on small scale with 2 baking equipments on last April.
  On last September large-scale works with 4 baking equipments started.
Total output by last month (2013/2/28) is 481.
  Averaged daily output : 0.8 (small-scale), 2.0 (full-scale), 1.4 (total)
  Averaged weekly output : 5.5 (small-scale), 13.9 (full-scale), 10.0 (total)
2013/3/4 the 18th KEKB Accelerator Review Committee 9
Small-scale work
Large-scale work

## Slide 10: Baking 4 : Achieved pressure after baking
For almost all beam pipes, achieved pressures after baking are below 1×10-7 Pa.
  If achieved pressure is higher than 1×10-7 Pa, the beam pipe is baked again. (only 3 cases so far)
  Mass pattern after baking is not monitored. (Although 2 of 4 baking equipment have RGAs, we don’t use them.)
2013/3/4 the 18th KEKB Accelerator Review Committee 10
< 1
12 23 34 45 56 67 78 89 910
10 <
[x10-8 Pa]

## Slide 11: TiN coating 1 : Coting method
For SuperKEKB LER, it is an important issue to mitigate the electron cloud instability.
  In order to reduce the electron cloud, inner surfaces of almost all LER beam pipes are coated with TiN (except beam pipes with clearing electrodes).
  TiN coating tests had been performed and the coating method was established.
TiN coating is done by a DC magnetron sputtering of Ti in Ar and N2 atmospheres.
  A Ti cathode rod (-400 V) is set on the center axis of beam pipe (hung from the top on in case of the vertical type).
  Gases are supplied into the beam pipes uniformly though the Ti rod.
  Magnetic field (16 mT) is supplied by solenoid coils.
  Preliminary experiments were performed at a test stand to decide the coating parameters.
  Thickness of TiN coating : 200 nm (at least)
  Straight beam pipes are coated by vertical type and bent pipes are coated by horizontal type.
2013/3/4 the 18th KEKB Accelerator Review Committee 11
Test stand
Mass Spectrometer
Ar gas (2.0 Pa)
N2 gas (0.5 Pa)
Ti Cathode Rod (-400 V)
16 mT
Solenoid Coil
Mass Flow Controller
Solenoid Coil’s Power Source
Discharge Power Source
Gauge
Pumping System
Beam pipe

## Slide 12: TiN coating 2 : Facility (vertical)
2013/3/4 the 18th KEKB Accelerator Review Committee 12
5 vertical equipments for straight beam pipes were built last year.
  Large-scale work started on last September with 4 vertical equipments.
  1 equipment is backup and not available now.
  Beam pipe with a length up to 5.5 m can be coated.
  Short beam pipes and dummy pipes are connected to make total length 6 m.
  Two lines of the beam pipes can be mounted side-by-side in one equipment.
  Combination of hot-air oven and circulators are adopted for pre-baking.
  It is not available for bent beam pipes.
Dummy pipe for length tuning
Beam pipes
6 m
Two lines of beam pipes
5 coating equipments (vertical)

## Slide 13: TiN coating 3 : View from bottom and middle floor
2013/3/4 the 18th KEKB Accelerator Review Committee 13
Bottom floor
Middle floor
Hot air circulator
Solenoid coil
Pumping unit
Hot air circulator
Viewing port and camera at the bottom to observe discharge

## Slide 14: TiN coating 4 : View from top floor
2013/3/4 the 18th KEKB Accelerator Review Committee 14
Control desk
Mass flow controllers
Introduced gas line

## Slide 15: TiN coating 5 : Working process
2013/3/4 the 18th KEKB Accelerator Review Committee 15
Before coating (at Oho clean room)
  Visual check on the beam pipe.
  Putting blank flanges on pumping ports and BPM ports.
  Connecting beam pipes and dummy pipes for length tuning. (if necessary)
  Leakage test
  Installation of beam pipes on coating equipment.
In coating equipment
  Leakage test
  Pre-baking (150 C, 24 hours)
  TiN coating (Discharge duration : 80 min.)
After coating
  Filling with dry nitrogen up to atmospheric pressure.
  Dismantling beam pipes
  Installation of NEG pumps and BPM electrodes at Oho clean room.
  Baking
Leakage test before installation

## Slide 16: TiN coating 6 : Installation of beam pipes 1
2013/3/4 the 18th KEKB Accelerator Review Committee 16
Beam pipes are transported and installed on the coating equipment by crane.
Hinge assembly to get beam pipe upright

## Slide 17: TiN coating 7 : Installation of beam pipes 2
2013/3/4 the 18th KEKB Accelerator Review Committee 17
Beam pipes are transported and installed in the coating equipment by crane.

## Slide 18: TiN coating 8 : Installation of beam pipes 3
2013/3/4 the 18th KEKB Accelerator Review Committee 18
Ti cathode rod (6m) is also installed by crane.
Ti cathode
Introduced gas line
Insulator
Bellows for positioning of Ti cathode rod

## Slide 19: TiN coating 9 : Coating 1
2013/3/4 the 18th KEKB Accelerator Review Committee 19
Introduced gases : Ar (2.2 Pa), N2 (1.8 Pa)
Discharged current : 6.3 A
Required time : 5 min (Ti coating for base of TiN) + 75 min (TiN coating)
N2
Ar
H2
Ti coating
TiN coating
1x100
1x10-1
1x10-2
1x10-3
1x10-4
1x10-5
1x10-6
1x10-7
1x10-8
Partial Pressure [Pa]
Time
Partial pressure during discharge (just upstream of pumping unit)
View from viewport at the bottom
Ti cathode rod

## Slide 20: TiN coating 10 : Coating 2
2013/3/4 the 18th KEKB Accelerator Review Committee 20
Cu beam pipe coated with TiN
Electron microscopic image of TiN coating

## Slide 21: TiN coating 11 : Performance evaluation
2013/3/4 the 18th KEKB Accelerator Review Committee 21
SEY of Al samples coated with TiN at this facility were measured.
  It was confirmed that SEY of TiN coating drops to below 0.8 after electron irradiation (incident electron energy : 250 eV)
  It was also confirmed that the cylindrical cathode rod is available for grooved surface adopted in bent pipes.
0.72
1.1
0.9
0.5
2.2
1.3
Al samples before coating
TiN coated samples
Al flat
Al groove
By S. Terui
By S. Terui

## Slide 22: TiN coating 12 : Rate of coating output
Coating work started on last July.
  Coating work started on small scale with 1 coating equipment on last July.
  On last September large-scale works with 4 coating equipments started.
Total output by last month (2013/2/28) is 411.
  Averaged daily output : 1.0(small-scale), 1.9 (full-scale), 1.7 (total)
  Averaged weekly output : 6.9 (small-scale), 13.6 (full-scale), 11.8 (total)
2013/3/4 the 18th KEKB Accelerator Review Committee 22
Small-scale work
Large-scale work

## Slide 23: TiN coating 13 : Horizontal type 1
2013/3/4 the 18th KEKB Accelerator Review Committee 23
Horizontal coating equipments for bent beam pipes are in preparation now.

## Slide 24: TiN coating 14 : Horizontal type 2
2013/3/4 the 18th KEKB Accelerator Review Committee 24
Discharge test will be done this month
Large-scale work with 2 equipment will start on April.
Installation test of Ti cathode rod in bent pipe

## Slide 25: Troubles
2013/3/4 the 18th KEKB Accelerator Review Committee 25
We had some troubles especially in the early stage.
  Deformation (1 Cu pipe) and cracks (3 Al pipes) of pipes at welding lines.
    Caused by stress mainly added during crane works.
    Change in our assembly and handling processes to decrease stress.
    Damaged beam pipes will be repaired.
  Vacuum leak at a welding line between connection flange and pipe
    Repaired by extra welding
  Interruption of baking due to shutdown of pumps cased by earthquake or electrical outage.
    Returning to the starting point of baking.
  Melting of NEG pump (GP50) during activation
    Change in power feeding method.
  Abnormal discharge during TiN coating.
    Caused by insulation failure.
    Removal of coating from insulator.
  Difficulty reducing residual H2O in coating equipment .
    Removal of dust on the bottom of coating equipment.
We have a lot less trouble recently.
  MO flange (Al) has the quality to last long and we had no problem with it after coating and baking so far.
Crack at welding line
Melted NEG pump

## Slide 26: Future plan
2013/3/4 the 18th KEKB Accelerator Review Committee 26
Apr. 2013  Dec. 2013 : 390 beam pipes for LER and HER
Jan. 2014  Mar. 2014 : 80 beam pipes for Damping ring
April 2014  Dec. 2014 : 250 beam pipes for LER, HER and Damping ring

## Slide 27: Summary
2013/3/4 the 18th KEKB Accelerator Review Committee 27
Pre-installation works (coating and baking) started on last April.
  Large-scale works by 10 workers with 4 vertical coating equipments and 4 baking equipments started on last September.
  So far 411 beam pipes were coated and 481 beam pipes were baked.
  Though we had some troubles at the early stage, we have a lot less trouble recently and we are on schedule.
Horizontal coating facility will be operated on large scale from next month.
  Coating test will be performed this month.
During next fiscal year (April 2013 - March 2014), 470 beam pipes will be treated.