## Slide 1: TiN Coating and Baking of Beam Pipes
The 19th KEKB Accelerator Review Committee
March 3, 2014
Kyo Shibata (on behalf of KEKB Vacuum Group)
Magnetron discharge sputtering for TiN coating

## Slide 2: Introduction 1
What should we do before the installation of new beam pipes?
  For HER (e-) : Baking at the laboratory(not in-situ)
  For LER (e+) : Baking & TiN coating at the laboratory
  For Damping Ring : TiN coating at the laboratory
  For all beam pipes : assembling work (NEG pump , BPM electrode)
How many beam pipes should be processed?
  For HER (e-) : 180
  For LER (e+) : 1000 (of which  25 have electron clearing electrodes and TiN coating is unnecessary. )
  Damping Ring : 100
Pre-installation work (coating and baking) started on April 2012.
  “Pre-installation work” means:
    Bringing beam pipes to KEKB Oho Lab. from storage area -> Coating (3days) -> Baking (3days) -> returning the beam pipes to storage area
  Large-scale works by 10 workers started on September 2012.
2014/3/3 the 19th KEKB Accelerator Review Committee 2

## Slide 3
2014/3/3 the 19th KEKB Accelerator Review Committee 3
3-go-kan Bldg.
(You are here.)
Storage area
KEKB Oho Lab.
Returning the beam pipes to storage area
Bringing beam pipes to KEKB Oho Lab. from storage area
TiN Coating
Baking
LER beam pipe without electrode
Visual check on the beam pipe
HER beam pipe
LER beam pipe with electrode
Assembling
(NEG pump & BPM electrode)
Flow chart of
pre-installation work
KEKB Oho Lab.
KEK Tsukuba Campus
DR beam pipe
DR beam pipe

## Slide 4: Introduction 2
What we did after last KEKB Review are
  Setting up horizontal coating facility with 2 equipment systems for bent beam pipes.
  Coating and baking of 430 beam pipes for LER and HER, of which 111 beam pipes were bent pipe and coated by the new horizontal facility.
    Pre-installation works of 925 beam pipes were finished in total so far.
    More 450 beam pipes (LER and HER : 350, Damping Ring : 100) must be coated and baked by the end of this year.
  Modifying the horizontal coating facility for damping ring beam pipes. (in progress now)
Topics discussed in this talk are
  Baking & TiN coating facility (review)
  Status report on baking and coating works
  Working Schedule
2014/3/3 the 19th KEKB Accelerator Review Committee 4
Now

## Slide 5: Layout of Oho laboratory 1
Baking equipment : 2 long type (5 m) and 2 short type (3 m)
Vertical TiN coating facility with 4 equipment systems for straight beam pipes
Horizontal coating facility with 2 equipment systems for bent beam pipes
2014/3/3 the 19th KEKB Accelerator Review Committee 5
Clean room
16m
16m
Oho experimental deck (top view)
6.5 m
4.5mm
Baking equipment (long type)
Baking equipment (long type)
Baking equipment (short type)
Baking equipment (short type)
coating facility
(vertical)
Coating facility (horizontal)
stairway
stairway

## Slide 6: Layout of Oho laboratory 2
View from different place.
2014/3/3 the 19th KEKB Accelerator Review Committee 6
Clean room

## Slide 7: Baking 1 : Equipment
Hot-air heating method was adopted.
  Two beam pipes are mounted up and down in one hot-air oven.
  Hot-air oven consists of movable insulated walls and insulated frame.
  Hot air is circulated in the hot-air oven.
  Each pipe is evacuated by a turbo-molecular pump (0.3 m3/sec) during the baking.
2013/3/4 the 18th KEKB Accelerator Review Committee 7
Movable walls
Beam pipe
(double decker)
Pumping unit
Hot-air circulator (7.5 kW)
Now baking
Short type
Long type

## Slide 8: Baking 2 : Baking conditions
Baking conditions
  Temperature : 150 C (120 C for beam pipes with electrodes)
  Baking period : 26 hours
    Temperature of the beam pipes in the oven became 150 C within a several hours.
  Targeted pressure after baking : < 10-7 Pa
  NEG pump is activated at the same time.
Before baking
  TiN coating (if necessary)
  Installation of NEG pumps and BPM electrodes at Oho clean room.
After baking
  Filling with dry nitrogen up to atmospheric pressure.
  Isolating the beam pipe and putting a blank flange on the beam pipe.
  Keeping the beam pipe in the storage area until the installation.
2013/3/4 the 18th KEKB Accelerator Review Committee 8
Storage area (Oho lab.)
Clean room

## Slide 9: Baking 3 : Baking output
Baking work started on April 2012.
Total output by last month (2014/2/28) is 925.
More 350 beam pipes must be baked by the end of November at the latest.
  Last year 367 beam pipes were baked in 7 months (from April to October).
  Baking work will restart from April.
2013/3/4 the 18th KEKB Accelerator Review Committee 9
Now we are here.
(waiting for new beam pipes.)

## Slide 10: Baking 4 : Achieved pressure after baking
2014/3/3 the 19th KEKB Accelerator Review Committee 10
For almost all beam pipes, achieved pressures after baking are below 1×10-7 Pa.
  If achieved pressure is higher than 1×10-7 Pa, the beam pipe is baked again.
  Mass pattern after baking is not monitored. (Though 2 of 4 baking equipment systems have RGAs, we don’t use them.)
< 1
12 23 34 45 56 67 78 89 910
10 <
[x10-8 Pa]

## Slide 11: TiN coating 1 : Coting method
For SuperKEKB LER and DR, it is an important issue to mitigate the electron cloud instability.
  In order to reduce the electron cloud, inner surfaces of almost all LER beam pipes are coated with TiN (except beam pipes with clearing electrodes).
  TiN coating tests had been performed and the coating method was established.
TiN coating is done by a DC magnetron sputtering of Ti in Ar and N2 atmospheres.
  A Ti cathode rod (-400 V) is set on the center axis of beam pipe.
  Gases are supplied into the beam pipes uniformly though the Ti rod.
  Magnetic field (16 mT) is supplied by solenoid coils.
  Preliminary experiments were performed at a test stand to decide the coating parameters.
  Thickness of TiN coating : 200 nm (at least)
  Straight beam pipes are coated by vertical type and bent pipes are coated by horizontal type.
2014/3/3 the 19th KEKB Accelerator Review Committee 11
Test stand
Mass Spectrometer
Ar gas (2.0 Pa)
N2 gas (0.5 Pa)
Ti Cathode Rod (-400 V)
16 mT
Solenoid Coil
Mass Flow Controller
Solenoid Coil’s Power Source
Discharge Power Source
Gauge
Pumping System
Beam pipe

## Slide 12: TiN coating 2 : Facility (vertical)
2013/3/4 the 18th KEKB Accelerator Review Committee 12
Straight beam pipes are coated by vertical facility with 4 equipment systems..
  Ti cathode is hung from the top of the pipe.
  Beam pipe with a length up to 5.5 m can be coated.
  Short beam pipes and dummy pipes are connected to make total length 6 m.
  Two lines of the beam pipes can be mounted side-by-side in one equipment.
  Combination of hot-air oven and circulators are adopted for pre-baking.
  It is not available for bent beam pipes.
  Large-scale work started on September 2012.
Dummy pipe for length tuning
Beam pipes
6 m
Two lines of beam pipes
Vertical coating facility

## Slide 13: TiN coating 3 : Facility (horizontal)
2014/3/3 the 19th KEKB Accelerator Review Committee 13
Bent beam pipes are coated by horizontal facility with 2 equipment systems.
  Basically, horizontal equipment has the same structure with vertical equipment.
  Beam pipes lie down in the solenoid coils.
  Ti cathode is set horizontally on the center axis of beam pipe by the ceramics supports with wheels.
  Large-scale work started on April 2013.

## Slide 14: TiN coating 4 : Working process
2014/3/3 the 19th KEKB Accelerator Review Committee 14
Before coating (at Oho clean room)
  Visual check on the beam pipe.
  Putting blank flanges on pumping ports and BPM ports.
  Connecting beam pipes and dummy pipes for length tuning. (if necessary)
  Leakage test
  Installation of beam pipes on coating equipment.
In coating equipment
  Leakage test
  Pre-baking (150 C, 24 hours)
  TiN coating (Discharge duration : 80 min.)
After coating
  Filling with dry nitrogen up to atmospheric pressure.
  Dismantling beam pipes
  Installation of NEG pumps and BPM electrodes at Oho clean room.
  Baking
Leakage test before installation

## Slide 15: TiN coating 5 : Coating 1
2014/3/3 the 19th KEKB Accelerator Review Committee 15
Introduced gases : Ar (2.2 Pa), N2 (1.8 Pa)
Discharged current : 6.3 A
Required time : 5 min (Ti coating for base of TiN) + 75 min (TiN coating)
N2
Ar
H2
Ti coating
TiN coating
1x100
1x10-1
1x10-2
1x10-3
1x10-4
1x10-5
1x10-6
1x10-7
1x10-8
Partial Pressure [Pa]
Time
Partial pressure during discharge (just upstream of pumping unit)
Ti cathode rod
Vertical type
Horizontal type

## Slide 16: TiN coating 6 : Coating 2
2014/3/3 the 19th KEKB Accelerator Review Committee 16
Electron microscopic image of TiN coating
Beam pipe (bent type) was successfully coated.
Though the color of the ceramic support was changed, insulation breakdown did not occurred.

## Slide 17: TiN coating 7 : Performance evaluation
2014/3/3 the 19th KEKB Accelerator Review Committee 17
SEY of Al samples coated with TiN at this facility were measured.
  It was confirmed that SEY of TiN coating drops to below 0.8 after electron irradiation (incident electron energy : 250 eV)
0.72
1.1
0.9
0.5
2.2
1.3
Al samples before coating
TiN coated samples
Al flat
Al groove
By S. Terui
By S. Terui

## Slide 18: TiN coating 8 : Modification for DR 1
2014/3/3 the 19th KEKB Accelerator Review Committee 18
Coating of beam pipes for DR are done by the horizontal facility.
New Ti cathode plate with the same curvature as the beam pipe is required.

## Slide 19: TiN coating 9 : Modification for DR 2
2014/3/3 the 19th KEKB Accelerator Review Committee 19
Modification for DR is nearly done.
Coating work will start soon.

## Slide 20: TiN coating 10 : Coating output
2014/3/3 the 19th KEKB Accelerator Review Committee 20
Coating work started on July 2012.
Total output by last month (2014/2/28) is 805.
More 280 beam pipes (LER:180, DR:100) must be coated by the end of this year.
  Last year 345 beam pipes were coated in 7 months (from April to October).
  LER : From April to October at the latest.
  DR : March, November and December.
Now we are here.
(modifying the horizontal facility and waiting for new beam pipes.)
Damping ring (100)
LER (180)

## Slide 21: Summary
2014/3/3 the 19th KEKB Accelerator Review Committee 21
Pre-installation works (coating and baking) started on April 2012.
  Large-scale works by 10 workers started on September 2012.
  Coating of bent beam pipes started on last April by the horizontal coating facility
  Pre-installation works of 925 beam pipes were finished in total, of which 111 beam pipes were bent pipe and coated by the horizontal facility.
Pre-installation work has been performed well so far without any serious problems.
  Though many connection flanges (MO flange) required treatment for scratches on the vacuum sealing surfaces after coating, this problem was solved by burnishing sealing surfaces with hand.
  Pre-installation work is almost on schedule so far.
  Modifying the horizontal coating facility for damping ring beam pipes is in progress now.
  Coating work will start soon.
By the end of this year, 450 beam pipes must be baked and coated.
  LER and HER (350): From April to November at the latest.
  Damping Ring (100): March, November and December.
  “450 beam pipes” seem to be an achievable goal.